## Build Tracker
# | Milestone | Step | Verification checkpoint (what "done" looks like) | Screenshot needed? | What to screenshot | Status | Date completed | Notes
M0 | Environment Setup | Provision Azure VM (Windows 11, 16GB RAM) | VM shows as Running in Azure Portal | No |  | Done
M0 | Environment Setup | Connect to VM via RDP | Windows 11 desktop visible and usable | No |  | Done
M0 | Environment Setup | Install Git for Windows | 'git --version' prints a version number | No |  | Done
M0 | Environment Setup | Install Python 3.12 | 'python --version' prints Python 3.12.x | No |  | Done
M0 | Environment Setup | Install Claude Code | 'claude --version' prints a version number | No |  | Done
M0 | Environment Setup | Clone GitHub repo, launch Claude Code inside it | Claude Code prompt shows C:\Projects\Research as working folder | No |  | Done
M1 | Library installation | Create virtual environment, install sentence-transformers, faiss-cpu, beautifulsoup4, requests, streamlit, pandas | Test script prints "all imports working" | Yes | Terminal output showing "all imports working" | In Progress
M2 | Corpus acquisition | Git-clone 1-2 Microsoft Learn docs repos (e.g. entra-docs) | Script counts and lists cloned markdown files (expect hundreds) | Yes | File count / listing output | Not Started
M3 | Content extraction & chunking | Parse markdown into clean, paragraph-level text chunks | 3 sample chunks printed read as clean prose, not raw markdown | Yes | Sample of 3 printed chunks | Not Started
M4 | Core proof of concept | Embed chunks with SBERT, build FAISS index | Index builds with no errors, reports chunk count | No |  | Not Started
M4 | Core proof of concept | Query with one test snippet, retrieve closest match + similarity score | Top match is genuinely relevant; score is sensible (not 0.0 or 1.0) | Yes | THE key screenshot — similarity score + matched passage | Not Started
M5 | Remaining signals | Build terminology drift signal | Test run returns a score + reason for one article | Yes | Score + reason output | Not Started
M5 | Remaining signals | Build broken links signal | Test run returns a score + reason for one article | Yes | Score + reason output | Not Started
M5 | Remaining signals | Build deprecated tech signal | Test run returns a score + reason for one article | Yes | Score + reason output | Not Started
M5 | Remaining signals | Build temporal metadata signal | Test run returns a score + reason for one article | Yes | Score + reason output | Not Started
M6 | Aggregation & explanation | Weighted aggregation of all 5 signal scores | One combined Knowledge Decay Score produced from 5 inputs | No |  | Not Started
M6 | Aggregation & explanation | Plain-language explanation generator | Full pipeline run end-to-end on one article from the command line | Yes | Final score + explanation, full pipeline output | Not Started
M7 | Streamlit UI | Build paste-URL/text input, submit button, results display | App launches locally in browser | No |  | Not Started
M7 | Streamlit UI | Submit a real test article through the browser | Correct score and explanation appear on screen | Yes | Browser screenshot: submitted article + displayed result | Not Started
M8 | Evaluation dataset & batch harness | Construct 40-60 labelled articles (genuine + synthetic decay) | Dataset file complete with ground-truth labels | No |  | Not Started
M8 | Evaluation dataset & batch harness | Build and run batch evaluation script | Precision/recall/F1 computed across full dataset | Yes | Metrics table (precision/recall/F1) | Not Started
M8 | Evaluation dataset & batch harness | Run ablation study (each signal removed in turn) | Comparison table showing performance with/without each signal | Yes | Ablation study results table | Not Started